## How to Use
WMS Implementation Roadmap — Template
Shiprocket WMS Rollout
This workbook is a reusable template for planning and tracking the end-to-end rollout of the WMS — from initial setup through training, documentation, pilot, and phased seller onboarding to full go-live. Sample entries are included in each sheet to show how to fill it in; replace them with your own plan.
Sheets in this workbook:
Sheet | Purpose
Roadmap | The master plan: one row per activity/milestone, grouped by phase and workstream, with owner, dates, status, dependency and exit criteria. This is the sheet you update weekly.
Seller Onboarding Ramp | Wave-by-wave plan for scaling the number of sellers (and warehouses) live on the WMS after the pilot, with cumulative coverage.
Status Legend | Reference for the Status values used in the Roadmap sheet and their meaning.
How to use it:
1. Rename/add rows in Roadmap for your own activities — keep the Phase column values consistent so grouping stays clean (or edit the phase list to match your org's terminology).
2. Set Status using the dropdown-style values in Status Legend — the cell will auto-colour.
3. Update the Seller Onboarding Ramp sheet as each wave's target is agreed with Ops/Business.
4. Use filters (already enabled on the Roadmap header row) to slice by Phase, Owner or Status for status-review meetings.

## Roadmap
Phase | Workstream | Activity / Milestone | Description | Owner | Start Date | End Date | Status | Dependency | Success Criteria / Exit Metric
1. Planning & Setup | Program Management | Project kickoff & governance setup | Confirm sponsors, steering committee, RACI and weekly review cadence. | Program Lead | 2026-06-01 | 2026-06-05 | Done | — | Steering committee formed; charter signed off
1. Planning & Setup | Infrastructure | WMS environment provisioning (UAT + Prod) | Set up hosting, integrations (OMS/ERP), and access roles for UAT and Production. | IT / Infra | 2026-06-03 | 2026-06-12 | Done | Kickoff complete | UAT & Prod environments accessible to core team
1. Planning & Setup | Process Design | Finalize SOPs for inbound / putaway / outbound | Document target-state warehouse processes the WMS will enforce. | Ops Design Lead | 2026-06-08 | 2026-06-20 | Done | — | SOPs reviewed and signed off by Ops Head
1. Planning & Setup | Pilot Planning | Select pilot warehouse & pilot sellers | Choose 1 warehouse and 2 low-complexity sellers to run the first live pilot. | Program Lead | 2026-06-15 | 2026-06-22 | In Progress | SOPs finalized | Pilot site + seller list agreed with Ops & Business
2. Training & Enablement | Trainer Enablement | Train-the-trainer session (supervisors) | Certify warehouse supervisors as in-house trainers for floor staff. | L&D Lead | 2026-06-23 | 2026-06-25 | Not Started | SOPs finalized | 100% of pilot-site supervisors certified
2. Training & Enablement | Floor Training | Operator training — scanning, putaway, picking | Hands-on training for warehouse operators on core WMS transactions. | Trainer / Supervisor | 2026-06-26 | 2026-06-29 | Not Started | Train-the-trainer done | All pilot-site operators pass floor assessment
2. Training & Enablement | Back-Office Training | Admin & back-office training | Masters management, reports, exception handling for admin users. | Trainer | 2026-06-26 | 2026-06-28 | Not Started | Train-the-trainer done | Admin users independently complete daily close-out
2. Training & Enablement | Refresher | Post-pilot refresher training | Re-train on flows revised after pilot feedback, before scale-up. | Trainer | 2026-07-20 | 2026-07-22 | Not Started | Pilot review complete | Refresher attendance ≥ 95% of pilot-site staff
3. Documentation | User Manuals | Role-based user manuals (Operator / Supervisor / Admin) | Step-by-step manuals per role, aligned to actual configured screens. | Documentation Lead | 2026-06-20 | 2026-06-27 | In Progress | SOPs finalized | Manuals published and linked from in-app help
3. Documentation | Floor Aids | Quick-reference / SOP cards for the floor | Laminated one-pagers at each station for the most common transactions. | Documentation Lead | 2026-06-24 | 2026-06-28 | Not Started | SOPs finalized | Cards placed at every station before pilot go-live
3. Documentation | Video Guides | Short video walkthroughs of key flows | 2–3 min screen-recorded walkthroughs for GRN, putaway, pick, pack, dispatch. | Documentation Lead | 2026-06-25 | 2026-07-02 | Not Started | User manuals drafted | Videos available in help center for all core flows
3. Documentation | FAQ | FAQ & troubleshooting guide | Common errors and resolutions, sourced from UAT and early pilot issues. | Support Lead | 2026-07-01 | 2026-07-10 | Not Started | Pilot go-live | Top 20 support queries answered without escalation
4. Pilot (On-Ground) | Go-Live | Pilot go-live — 1 warehouse, 2 sellers | Cut over pilot warehouse operations to WMS for the selected sellers. | Program Lead | 2026-06-30 | 2026-06-30 | Not Started | Training complete | Pilot live with zero P0 issues on day 1
4. Pilot (On-Ground) | Hypercare | Daily on-ground hypercare support | War-room support on the floor for first 2 weeks post go-live. | Support + Product | 2026-06-30 | 2026-07-14 | Not Started | Pilot go-live | SLA adherence ≥ 95% during hypercare window
4. Pilot (On-Ground) | Review | Pilot performance review (SLA, errors, adoption) | Assess pilot against agreed KPIs: order SLA, mis-pick rate, adoption %. | Program Lead | 2026-07-15 | 2026-07-17 | Not Started | 2 weeks hypercare data | KPI scorecard reviewed with steering committee
4. Pilot (On-Ground) | Sign-off | Pilot sign-off & go/no-go for scale-up | Formal decision to proceed to phased seller onboarding. | Steering Committee | 2026-07-18 | 2026-07-18 | Not Started | Pilot review complete | Go/no-go documented and communicated
5. Stabilization & Feedback | Defect Fixes | Fix P0/P1 issues raised during pilot | Triage and close blocker/high-severity issues before scaling further. | Engineering | 2026-07-15 | 2026-07-24 | Not Started | Pilot review complete | Zero open P0/P1 defects at scale-up start
5. Stabilization & Feedback | Process Refinement | Incorporate pilot process learnings | Update SOPs/config based on what broke or was confusing in pilot. | Ops Design Lead | 2026-07-18 | 2026-07-24 | Not Started | Pilot review complete | Revised SOPs approved for Wave 1
5. Stabilization & Feedback | Learnings Report | Publish pilot learnings report | Document what worked, what didn't, and changes made, for stakeholders. | Program Lead | 2026-07-23 | 2026-07-25 | Not Started | Process refinement done | Report circulated to steering committee
6. Phased Seller Onboarding | Wave 1 | Onboard next 5 sellers (same warehouse) | Extend live WMS usage to 5 additional low/medium-complexity sellers. | Onboarding Lead | 2026-07-28 | 2026-08-08 | Not Started | Pilot sign-off | 5 sellers live, SLA within 5% of pilot baseline
6. Phased Seller Onboarding | Wave 2 | Onboard next 15 sellers + 2nd warehouse | Scale to a second warehouse and a broader seller mix. | Onboarding Lead | 2026-08-11 | 2026-08-29 | Not Started | Wave 1 stable | 22 sellers live across 2 warehouses
6. Phased Seller Onboarding | Wave 3 | Onboard next 30 sellers + 3rd warehouse | Continue geographic and seller-complexity expansion. | Onboarding Lead | 2026-09-01 | 2026-09-26 | Not Started | Wave 2 stable | 52 sellers live across 3 warehouses
7. Full Rollout & BAU | Full Go-Live | Remaining sellers live on WMS | Onboard all remaining sellers across the full warehouse network. | Onboarding Lead | 2026-10-01 | 2026-10-24 | Not Started | Wave 3 stable | 100% of sellers live on WMS
7. Full Rollout & BAU | Handover | Hypercare handover to steady-state support | Transition from project hypercare to standard support/on-call model. | Support Lead | 2026-10-25 | 2026-10-31 | Not Started | Full go-live | Support runbook adopted; on-call rota live
7. Full Rollout & BAU | Decommission | Legacy system decommission / parallel-run exit | Switch off or archive the legacy WMS/manual process. | IT / Infra | 2026-11-01 | 2026-11-10 | Not Started | Hypercare handover | Legacy system read-only or decommissioned
7. Full Rollout & BAU | Benefits Review | Post go-live review & benefits realization | Compare actual SLA/cost/productivity gains against the original business case. | Program Lead | 2026-11-15 | 2026-11-21 | Not Started | Decommission complete | Benefits report signed off; program formally closed

## Seller Onboarding Ramp
Wave | Target Date | New Sellers Added | Cumulative Sellers Live | Warehouses Live | Order Volume Covered (%) | Notes
Pilot | 2026-06-30 | 2 | 2 | 1 | 3% | Low-complexity sellers, single warehouse
Wave 1 | 2026-08-08 | 5 | 7 | 1 | 10% | Extend within pilot warehouse
Wave 2 | 2026-08-29 | 15 | 22 | 2 | 35% | Adds 2nd warehouse
Wave 3 | 2026-09-26 | 30 | 52 | 3 | 65% | Adds 3rd warehouse; mixed complexity
Full Rollout | 2026-10-24 | 48 | 100 | 4 | 100% | All sellers, full network live

## Status Legend
Status values used in the Roadmap sheet
Status | Meaning
Not Started | Activity is planned but work has not begun.
In Progress | Actively being worked on.
Done | Completed and verified.
Blocked | Cannot proceed — dependency or issue needs resolution.